## Sheet1
Oulton Parish Council - Deadline 8 Submission.
Appendix 1. Abnormal Load Delivery Likely Scenarios.
Week 1 | Week 2 | Week 3 | Week 4 | Week 5
36 cable drums from port to Main Compound | 12 Cable drums delivered to cable route | 12 Cable drums delivered to cable route | 12 Cable drums delivered to cable route | 36 cable drums from port To Main Compound
Night deliveries (23.00-07.00)** | 07.00-23.00 | 07.00-23.00 | 07.00-23.00 | Night deliveries (23.00-07.00)**
Originally advised by Orsted 8-12 a day/3-4 days | Outside of peak hours 07.45-08.45/17.15-18.15 | Outside of peak hours 07.45-08.45/17.15-18.15 | Outside of peak hours 07.45-08.45/17.15-18.15 | Originally advised by Orsted 8-12 a day/3-4 days
LIKELY Scenario 7/8 a night over 5 days | 3 a day /4 days## | 3 a day/4 days## | 3 a day/4 days## | LIKELY Scenario 7/8 a night over 5 days
8 hours window | 14 hour window | 14 hour window | 14 hour window | 8 hours window
**Night time deliveries will be the most intensive when the 36 cable drums are delivered TO the Main Compound in one week resulting in 7/8 a night over 5 days.
##Week 2,3,4 deliveries FROM the main compound TO the cable route would be 3 a day over 4 days, which would mean a potential delay of 5mins 42 seconds, 3 times a day, for the B1149 dependent on time of day.
**This scenario would be repeated until 1,121 cable drums had been deliverd TO the Main Construction Compound and then OUT again to the cable route in the 30 month active construction period